## Sheet1
Strategic Initiative 1: Optimize the First Year Experience
Action | Implementation Lead | Partners | Completion & Timing | Deliverables | Resource Needs | Measures (KPIs) | Progress to Date
1.1 Create a New Student Experience Framework that maps intentional co-curricular student engagement and learning opportunities throughout the entire first-year experience. This framework will be developed in partnership with Academics and Student Services, working together to support academic transition and wholistic student success. Build Understanding | • VP, Students + Co-Executive Sponsor (Academics) | • FYE Working Group • Director, Student Life •Student Development | • 1-12 months | • Assemble FYE Working Group, including faculty members. Create Terms of Reference • Dedicate administrative support to research; develop discussion paper to provide evidence-based context and direction, including understanding current FY transitions experiences (ex. CCWS, ISS) • In partnership with Academics, organize FY faculty meetings to better understand the transitional needs of students as they appear in the classroom. |  | • Number of FYE Working Group members • Number of meetings per year • Number of first year faculty engaged in discussion | IN PROGRESS • Assembled FYE Working Group to inform FY transitions programs. • Partnered with Academics to organize meeting of Student Services providers and faculty who teach first-year courses. The aim is to understand transitional needs appearing in the classroom, and identify opportunities to provide tailored services, supports and programs to faculty, staff and students. • Developing plan for regular and ongoing discussions with faculty.
1.2 Collaborate with the Students' Union, academic units and other campus and community partners to develop and deliver an evidence-informed Orientation program, based in student flourishing. Identify and remove barriers to participation in Orientation Week. Integrate opportunities to learn about and share diverse cultural identities and create a welcoming community of authentic belonging. Build Understanding | • VP, Students + Co-Executive Sponsor | • FYE Working Group • Students' Union • Student Life • Residence Life • Athletics | • 1-3 years | • Develop and deliver comprehensive student leader orientation and training program • Track completed assessment of participant learning and growth | • Personnel Time • Programming Supplies • Employee Compensation (ex. CE) • Hiring and Training Materials | • Number of co-curricular transitions programs offered in residence, on-campus. • Number of students participating in Orientation Week and extended orientation programs • Number of students participating in residence programs • Assessment of participant learning and growth | IN PROGRESS • In 2022, StFX launched Flourishing Foundations, a series of co-curricular programs designed to support student transition to StFX. • Reviewed and revised residence programming model, with a focus on supporting first-year orientation and transition. • Revised House Council structure and created Community Educator (CE) roles in residence, to provide leadership opportunities for first-year students and enhance transitions programming in residence. Provided training and ongoing professional development. • Piloting 'radical welcome' for students from historically-excluded groups, in collaboration with Office of Internationalization. • Updated the Community Code of Conduct and created new Residence Standards, with a focus on the relational approach and committment to restorative practices • In collaboration with the Students' Union, extended the number of substance free social events throughout the first six weeks.
1.3 Embed equity, anti-racism and accessibility in the development and execution of special student-facing events and programming (Extended Orientation Programming, Homecoming, etc.), representing the diverse lived experiences and identities present in our university community. Build Understanding | • Director, Student Life | • SSLT • DEC • HRERA | • 1-3 years | • Assemble First-Year Experience Working Group to coordinate incoming student transition, including students from historically-excluded groups. • Establish Working Group to focus on transitions experiences for historically-excluded groups. • Evaluate existing orientation events and programs, through an equity and anti-racism lens. • Consider the addition of new programming designed to support transition for Mi'kmaw, Indigenous and Black students. | • Dedicated program funding • Training materials *Opportunity to seek government and/or donor funding | • Number of first-voice perspectives engaged in the process • Number of students from historically-excluded groups participating per year • Assessment of participant learning and growth | IN PROGRESS • Assembled a First Year Experience Working Group to review and develop transitions programming. • Population-specific transitions programming offered during Orientation Week 2022, including opportunities to connect with supports and services
1.4 Develop high-quality co-curricular and peer learning experiences and transitions programming for off-campus, mature, distance learning, transfer students and student athletes that enrich their student experience. Build Understanding | • Director, Student Life | • Student Development • Program Tean | • 1-3 years | • Deliver programs to all students, orienting them to resources, suports and services • Consult a needs assessment and recommendations to meet the current transitions experiences of each group. • Identify opportunities to improve current transitions programs to meet diverse student needs. Consider developing tailored transitions programs to meet unique needs for each group. | • Programming Materials • Promotions Materials • Employee Compensation (i.e., development of CE roles for specialized populations, including distance, grad and transfer students) | • Number of transitions programs delivered • Number of students participating per year • Assessment of participant learning and growth | IN PROGRESS • Partnered with Academics to develop and implement X-Academic Transitions Program (X-ACT), open to all first year and transfer students. This program is part of Flourishing Foundations. • Dedicated communications to transfer and mature students living in residence, inviting them to events and programs.
1.5 Develop online videos/modules for parents/supporters to be empowered to support their student in their transition to university and throughout their first-year experience. These same tools will be used for faculty, staff and students to understand the supports available and how to access, and when. Build Understanding | • Student Development • Communications | • HRERA • SVPRA • Wellness Education • Health and Counselling | • 1-2 years | • Developing online resources for parents/supporters | • Virtual platform (ex. Greenspace) • Video production | • Number of resources offered • Number of unique users accessing web content • Number of resource downloads | IN PROGRESS • StFX Student Services as contracted GreenSpace to develop a centralized 'hub' for mental health and wellness supports and services. The resource is accessible to students, parents/supporters.
1.6 Leverage the ‘Being Xaverian’ campaign as an opportunity to share Xaverian community values and collect and share stories of diverse student experiences at StFX. Build Understanding | • Student Development | • Marketing and Communications • Manager, Restorative | • 1-12 months | • Develop campaign content and ongoing communications strategy | • Personnel Time • Promotions Materials • Virtual Platform • Employee Compensation (i.e., dedicated communications support for StFX Student Services). | • Identification of student stories to highlight each year • Completed article/story posted to web • Completed communication regarding feature on web • Number of students participating • Percentage of community stakeholders accessing content | IN PROGRESS • Developed campaign content and ongoing communications plan to promote Being Xaverian
1.7 Provide proactive programming and experiential initiatives that support harm reduction approaches to substance use and provide healthy alternatives to socializing. Build Understanding | • Director, Student Life | • Manager, Restorative | • 1-12 months | • Develop and implement a substance strategy, to align with PEP-AH and with continued emphasis on sexual violence prevention and response. | • Employee Compensation (Peer Mentor) • Programming Supplies • Promotions Materials * Opportunity to seek government and/or donor support. | • Number of programs per year • Tracking number of participants • Assessment of participant learning and growth | IN PROGRESS • In collaboration with the Students' Union, extended the number of substance free social events throughout the first six weeks. • Developed and launched Xaverian Community Foundations modules offered to all first-year students and again to some student leaders (ex. CAs), including anti-racism module (You Belong @X). • Created Community Educator (CE) roles in residence, to provide alternate programming and events in residence. • Initiated extended orientation and transitions programs, to provide alternate events and programming (ex. Bloomfield Hub). • Initiated Standing Committee of StFX University, Town and County, Landlords, RCMP to work collaboration in support of harm reduction approaches.
1.8 Collaborate with Academics to establish a transition year program to support student success (both pre-entrance and during first year), including formal (e.g., campus and courses) and informal supports (e.g., mentorship). This should include: • A Summer Bridge Program focused on academic orientation, community connection, strengths assessment, and connection with local communities. • Tailored programming and engagement opportunities for students from historically-excluded groups. • Ability to obtain ESL training and supports for international students and other students for whom English is not their first language Build Capacity | • VP, Students | • FYE Working Group + Subcommittee • SSLT/ALT • Student Development • Program Team | • 1-3 years | • Assemble a FYE Working Group, with sub-committee focused on transitions experiences for historically-excluded groups. • Develop program model and implementation strategy, informed by student needs and evidence-informed practices. • Pilot a transition year program for Mik'maw, Indigenous and Black highschool students to transition to undergraduate programs at the University. Ensure that the program is accessible to all students and connected to surrounding communities. • In partnership with Academics, explore additional transitions opportunities (ex. awards, for-credit courses). | • Personnel Time • Programming Supplies • Promotions Materials * Opportunity to seek government and/or donor support. | • Number of individuals with lived experiences engaged in the process • Number of students from historically-excluded groups participating per year • Assessment of participant learning and growth | IN PROGRESS • In 2022, StFX launched Flourishing Foundations, a series of co-curricular programs designed to support student transition to StFX. • In Sep 2022, the Diversity Engagement Centre lauched a peer mentorship program for students from historically-excluded groups. • Partnered with Academics to develop and deliver X-Academic Transitions (X-ACT), open to all first-year and transfer students. • Additional transitions supports include pre-university preparation courses (ex. Math Prep) offered by Continuing and Distance Education
1.9 Coordinate a Winter Transitions program to welcome new students arriving in January (often these students are international students), and re-orient all first-year students to the programs, services and supports provided by StFX. Build Understanding | • Director, Student Life | • Student Development • Residence Life • Program Team | • 1-2 years | • Partner with StFX Students' Union to offer Societies' Fair in January • Develop and enhance residence programming and communications to welcome new students in arriving in January | • Programming Materials • Promotions Materials | • Number of transitions programs delivered • Number of students participating per year • Assessment of participant learning and growth | IN PROGRESS • Assembled FYE Working Group to inform FY transition. • Reviewed and revised residence programming model, including enhanced transitions programming in January. • Partnered with Students' Union to support and enhance programming during Frost Week.
1.10 Build capacity for the Residence Life Leadership Team, Diversity Engagement Centre, Bloomfield Hub, and other student peer leaders to frontload developmental mentorship and coaching in support of first-year transition and student success. Mentors will have the capacity to provide strengths-based coaching, using an equity lens. Build Capacity | * VP, Students * SSLT | * Administration * Student Development * Residence Life * DEC * Career Services * Health and Counselling | • 1-3 years | * Define developmental mentorship and identify required skillsets * Develop a scaffolded training program for all student leaders on campus, including a combination of online and in-person training sessions | • Employee compensation (Peer Mentor, Grant Funded) • Training and professional development costs (ex. CDM, MHRFA, Clifton Strengths) | • Number of training sessions delivered per year • Number of participants completing training • Completed assessment of participant learning and growth | IN PROGRESS • Transitioned RLC to live-in roles, with additional staff support • Developed new RLC onboarding process, with a focus on mentorship skills development • Created Senior Community Advisor (SCA) position to provide mentorship to student staff and community • Revising SCA/CA training program, with a focus on mentorship skills development • Implemented Incoming Student Survey (ISS) to help mentors understand student needs
1.11 Create group mentoring networks for students from historically excluded groups to come together in community, share experiences and explore academic, personal and career opportunities and pathways. This includes Indigenous, Black, minoritized, 2SLGBTQIA+ students, international students, new Canadians, first-generation students and students with disabilities. Build Connection | • Director, Human Rights and Equity | • DEC • Tramble Centre for Accessible Learning | • 1-12 months | • Identify opportunities to integrate mentorship opportunities into the suite of transitions programming available to students from historically-excluded groups • Promote opportunities for students to participate in existing mentorship programs, including X Connects • Identify opportunities to connect students to informal community networks, promote connections to existing communities. | Facilitators Session Supplies Promotions Materials | • Number mentors • Number of mentees • Assessment of participant learning and growth *Potential for government and/or donor support | IN PROGRESS • In 2021, launched Alumni Mentorship Program (X-Connects) to connect students with personal and career mentors. • In 2022, launched Diversity Engagement Centre (DEC) mentorship program for students from historically-excluded groups, including lndigenous, Black and 2SLGBTQIA+
1.12 Build on and promote existing mentorship networks of StFX faculty, alumni and Career Services and community networks to ensure all StFX students have opportunities to seek career mentors from a diverse network. Build Connection | • Director, Student Life | • Student Development • Career Services • Alumni | 1-3 years | • Identify opportunities for community partnerships to expand mentorship opportunities (ex. Mentoring Plus) • Develop and implement and communications strategy to promote mentorship opportunities | • Peer Mentor (grant funded) | • Number of participating mentors • Number of participating mentees • Evaluation of participant learning and growth | IN PROGRESS • In partnership with StFX Alumni, launched X-Connects Peer Mentorship Program • Convened working group to explore opportunities to integrating community partnerships (i.e., Mentoring Plus) into the existing suite of mentorship programs available to StFX students.
Strategic Initiative 2: Strengthen Mental Health Supports and Services
Action |  |  | Timeframe | Deliverables | Resource Needs | Measures (KPIs) | Progress to Date
2.1 Strengthen awareness of full range of students resources and the ways to access those resources. Ensure students have information about mental health and addictions services, critical care, after hours care, and local community resources. Build Understanding | • VP, Students • Director, Health and Counselling | • Administration • Student Development • Communications | • 1-12 months | • Enhance digital content (social media, web) • Establish scope and definition of non-clinical case manager (BSW), in collaboration with academics. • Provide staff training on applying case management approach. • Offer complementary supports for off-campus students. | • Web redesign, virtual platform • Promotions materials • Employee compensation (i.e., Non-Clinical Case Manager) • Professional development and training costs | • Number of unique users accessing web content • Number of unique users accessing collateral communications content (social media, etc.) • Number of training sessions offered per year • Number of faculty and staff participating • Assessment of participant learning and growth | IN PROGRESS • Contracted Green Space Consulting to develop centralized webpage for programs, services and supports delivered by StFX Health and Counselling. • Created new Student Services webpage, that connects students to relevant resources and supports available on-campus and off-campus. • Communications content developed and delivered.
2.2 Develop tools and resources to support administrative leaders, faculty, staff and students in identifying signs and symptoms of distress or at-risk behaviours, and competencies in helping others by supporting those in need in accessing appropriate resources. Build Understanding | • Director, Health and Counselling | • Case Manager | • 1-3 years | • Provide training and professional development on embed culturally-relevant approaches to teaching and learning • Provide coaching and referral resources to support faculty who are concerned about a student. * Launch a short, online professional development module with accompanying Lunch and Learn sessions. * Develop 'blue folder' with tailored resources for faculty and staff * Work with Deans, Chairs and Coordinators to streamline internal referral pathways for students of concern. | • Training Supplies and Resources • Virtual Platform • Promotions Materials • Professional development and training costs * Opportunity to seek government and/or donor support. | • Number of unique users accessing web content • Number of unique users accessing collateral communications content (social media, etc.) • Number of training sessions offered per year • Number of faculty and staff participating • Assessment of participant learning and growth | IN PROGRESS • Contracted Green Space Consulting to develop centralized webpage for programs, services and supports delivered by StFX Health and Counselling • Offering additional sessions of Mental Health First Aid to faculty and staff • Offering Healthy Minds/Mental Health 101 videos • Developed series of education videos for faculty and staff, focused on sexual violence prevention and response.
2.3 Frontload transitional supports for all students that normalize help seeking behaviours and increase awareness about the resources available. Incorporate mental health and wellness literacy, development of resiliency, coping, and stress management skills, and awareness of campus supports and services within Orientation and Extended Orientation programming; build into graduate student orientations, varsity sports teams training, etc.
2.4 Create evidence informed frameworks that support our Residence Education programming, Alcohol and Substance Use Strategy and Mental Health & Wellness initiatives, ensuring that our programs are sensitive to diverse student experiences. Build Capacity | • Student Development | • Health & Counselling • Wellness Education • SV Prevention and Response Advocate | • 1-3 years | • Reinvigorate partnership with PEP-AH, committing StFX to the PEP-AH Framework • Remain engaged with provincial policy development and action group • Develop and promote consistent definition of harm reduction • Strengthen Xaverian Community Foundations: Safer Socializing Module, informed by PEP-AH Framework • Continue to expand residence programming model, providing program alternatives to promote healthy socializing. • Implement early intervention support and education. | • Program Funding • Promotions Materials • Support for managing PEP-AH committee and provincial initiatives | • Number of programs per year • Number of students participating per year | IN PROGRESS • Reviewed and revised residence programming model, with a focus on providing program alternatives to promote healthy socializing. • Establish and expanded Bloomfield Hub, with dedicated staff resourcing as part of StFX's Continuum of Care • Piloting Stress and Coping Workshop for first-year business students as part of an expanded mental health and wellness curriculum • Piloting Climate Action and Mental Health Student Discussion Program • Renewed PEP-AH & Alcohol Policy Coalition Memberships
2.5 Review existing student services policies, processes, practices and and procedures that may unintentionally discriminate, and revise policies through an EDIA lens. • Develop new policies and procedures, including: Leave of Absence Policy, Return to Campus Following Hospitalization or Emergency Transport procedures, Accommodations Policy for Episodic and Non-Permanent Injury or Illness, and Death of a Student. Build Capacity | • Director, Human Rights and Equity • Director, Health and Counselling | • Equity Committees • Tramble Centre for Accuessible Learning • Case Manager • SLT • Academics | • 1-3 years | • Convene meetings of committees and working groups to revise ToR, and create committee structure and process for policy review and development. | • Consultation costs (external reviewers) | • Number of policies reviewed, revised and created • Number of individuals with lived experiences engaged in the review process | IN PROGRESS • A comprehensive policy review using an intersectional lens is being conducted by Rainbow Diversity Institute which employs Black, queer individuals and persons with disabilities. The process is being led by HR & EHR and informed by the University’s Equity Advisory Committee. • Revised StFX Code of Conduct, in consultation with DEC and PACAR. • Reviewed and revised StFX Harassment and Discrimination Policy in 2021.
2.6 Streamline access to culturally relevant, trauma-informed supports and services available to students who have experienced acts of racism, harassment and/or discrimination. Special consideration should be given to those with intersecting identities (e.g., with differing sexual orientation and gender identities). • Explain counselling and health services intake processes with greater clarity. • Make information and resources about mental health easy to find, including one platform to learn about services and supports available on-campus and off-campus. • Ensure healthcare practitioners can provide culturally-responsible and safe services that are reflective of the diversity of students • Consult Mi'kmaw, Indigenous and Black individuals, members of historically-excluded community, and other relevant groups on an ongoing basis. Apply their feedback to continue to improve on-campus supports and services. Build Capacity | • Director, Health and Counselling • Director, Human Rights and Equity | • HRERA | • 1-3 years | • Culturally-relevant, trauma-informed counselling services are available to students, with consideration to those with intersecting identities. • StFX website is updated with information, specifying resources tailored to Mi'kmaw, Indigenous, and Black students. |  | • Number of appointments per year • Number of unique vs. recurring visits per year • Number of training sessions offered per year • Number of healthcare service providers participating per year • Assessment of participant learning and growth | IN PROGRESS • StFX offers culturally-relevant, trauma-informed mental health supports and services for Mi'kmaw, Indigenous and Black students, faculty and staff. These services are provided by counsellors with lived experiences, who are themselves members of these communities. • Students can connect with the Diversity Engagement Centre (DEC), including the Indigenous Student Advisor and Black Student Advisor • StFX Student Services as contracted GreenSpace to develop a centralized 'hub' for mental health and wellness supports and services.
2.7 Hire a Human Rights Education and Response Advocate (HRERA) position in the institution to advocate for students, faculty, and staff experiencing racism and support them in navigating reporting channels. Communicate clear pathways for how students, faculty, and staff can receive support and/or report incidents. Build Capacity | • Director, Human Rights and Equity | • HRERA |  | • Hire a Human Rights Education and Response Advocate (HRERA) to provide outreach, information, referrals, and support to students who are experiencing racism and helping them navigate the reporting process. • Provide information on how students can access the HRERA, communicating clear pathways for making a report and/or receiving support. | • Employee compensation • Training and professional development costs (ex. CDM, MHRFA, Clifton Strengths) | • Number of times students are referred to HRERA • Percentage of time seeking unique vs. recrurring students • Amount of time between referral and contact with HRERA | IN PROGRESS • In August 2022, Student Services hired a Human Rights Education and Response Advocate (HRERA). The HRERA receives, responds to, and manages disclosures of harassment and discrimination. They lead, coordinate, and promote equity awareness, prevention and education programs and strategies on campus.
2.8 Work with community members to develop informal resolution practices for individuals who do not wish to undergo formal reporting processes, which are inclusive of the cultures of historically-excluded communities. This may include those based on restorative justice principles, to address incidents of racism. Build Capacity | • Director, Student Life | • Manager, Restorative Practices • HRERA • SVPRA | 1-2 years | • Revise the StFX Student Community Code of Conduct, and other disciplinary policies and practices, through an equity and anti-racism lens. • Develop informal resolution practices for individuals who do not wish to undergo formal reporting processes. |  | • Number of incidents addressed through the StFX Community Code of Conduct • Proportion of incidents addressed through alternate resolution processes (ex. restorative practices) | IN PROGRESS • In September 2022, Student Services released a revised StFX Student Community Code of Conduct. The revised Code is informed by the principles of restorative practice. PACAR provided feedback on the draft document.
2.9 Complete a needs assessment and recommendations for accessibility supports and services, including services and supports available for students with temporary or episodic disabilities. Planning should include assessing staffing needs, funding structures, supervision, and accountability in relation to the goals outlined in the Accessibility Plan, new provincial accessibility standards, and the vision of 'all students flourishing'. Build Capacity | • VP, Students • Director, Health and Counselling | • Tramble Centre for Accessible Learning | 1-3 years: Tramble Centre for Accessible Learning | • Complete needs assessment and recommendations | • Consultation costs (external reviewers) | • Number of students using accessibility supports and services. • Number of first-voice perspectives engaged in the process. • Ongoing evaluation of accessibility improvements, including feedback from students with disabilities and those who experience barriers to accessibility. | TO BE DEVELOPED
2.10 Implement a case management model to support “students of concern”. This may include students with mental illnesses or students who may be experiencing mental distress, who are in academic difficulty or may be heading toward or experiencing a crisis. Case Management supports students who have complex or multifaceted situations requiring a coordinated response. Build Capacity | • VP, Students | • Student Life • Residence Life • Health and Counselling • Equity and Human Rights • Academics | 1-12 months | • Establish scope of non-clinical case manager (BSW), in collaboration with Academics. • Enhance training and professional development to professional staff (ex. RLCs, DEC, CAs) using case management approach. • Offer complementary supports for off-campus students. | • Employee compensation (i.e., Non-Clinical Case Manager) • Professional development and training costs | • Number of times a student is referred to a service by campus partners vs. community partners • Amount of time between referral and touch point with a support office • Percentage of time seeing unique vs. recurring students • Percentage of time spent in 1:1 appointments | IN PROGRESS • Developed Incoming Student Survey (ISS) to identify students in need of supports, and connection to the appropriate resources. • Established process for professional residence life staff (RLCs) to connect with 'Students of Concern'
2.12 Provide proactive "care for the student caregivers" mental health supports debriefing for student peer support workers who provide frontline and critical incident interventions to fellow students. Build Capacity | • Director, Student Life | • Manager, Residences • Health & Counselling | 1-12 months | • Develop and launch campaign to building understanding and awareness of existing after hours supports available to all students and student leaders • Develop a consistent definition of critical incident • Assess the needs of students in response to these incidents, and devise response strategies to meet their needs. |  |  | TO BE DEVELOPED • Residence Life has developed outreach standards approach. Some of the outreach standards include outreach for students following a critical incident in residence.
2.13 Identify and streamline pathways to care to support early identification, self-care, and help-seeking by putting students in contact with the appropriate resources at the appropriate time. Make changes to how existing health services are structured to match how students are accessing information and services. We prioritize reducing wait times; streamlining service pathways and follow-up for students, faculty and staff; and improved communications around resources and services. This initiative should include: • Expanding collaborative partnerships between StFX and health care agencies and community resources to systematize a coordinated approach to supporting wholistic student success and well-being. • Pilot mobile health unit to provide after-hours supports and services, in partnership with Nova Scotia Health Build Connection | • Director, Health and Counselling • VP, Students | • Nova Scotia Health • Administration • Case Manager • Health & Counselling • Student Life • Residence Life | • 1-12 months | • Work with St. Martha's Hospital and Nova Scotia Health to identify and provide community resources to which students can be referred during high-peak times. |  | • Number of students accessing mobile clinic • Number of times a student is referred to a service by campus partners vs. community partners • Percentage of time spent in 1:1 appointments | IN PROGRESS • Piloting mobile clinic program, connecting students with after hours physican care, with potential to expand to mental health.
2.14 Convene regular CARE Team meetings to formalize a coordinated, wrap around support model between faculty, academic units, and student services with systems and policies to facilitate communication and foster integrated and student-centric supports. The Care Team responds to reprorts about students experiencing difficulties of whose behaviour is raising concerns within the university community. Build Connection | • VP, Students | • Student Life • Residence Life • Health and Counselling • Equity and Human Rights • Manager, Restorative Practices • Academics | 1-12 months | • Establish CARE Team, include process for receiving referrals |  | • Number of CARE Team meetings per year • Number of cases referred to CARE team per year • Percentage of time discussing unique vs. recurring students | TO BE DEVELOPED
Strategic Initiative 3: Foster Early and Ongoing Engagement with, and Recognition of, Experiential Learning
Action | Implementation Lead |  | Completion & Timing |  | Resource Needs | Measures (KPIs)
3.1 Develop an integrated Experiential and Co-Curricular Learning Framework to scaffold intentional student learning and engagement opportunities through all programs and years of study. Build Understanding | • VP, Students + VP, Academics (Co-Executive Sponsors) | • Career Services • Service Learning • Residence Life • Athletics | • 1-2 years | • Establish Experiential and Co-Curricular Learning Working Group, including ToR • Working Group to establish shared learning goals, consistent across curricular and co-curricular learning opportunities • Identify and inventory existing experiential and co-curricular learning opportunities at StFX. | Personnel Time | • Number of Working Group members • Number of meetings per term | TO BE DEVELOPED
3.2 Review existing co-curricular programs, services and supports through an EDIA lens to meet the needs of both specific and broad intersectional student identities, including Indigenous, Black, minoritized, 2SLGBTQIA, international students, graduate student, mature students, and students with disabilities. Build Understanding | • VP Students • Governance and Strategic Initiatives | • Student Life • Residence Life • Health and Counselling • DEC • Career Services | • 1-2 years | • Develop and implement multiple assessment strategies to better understand diverse student experiences in co-curricular programs and services. • Use assessment surveys and focus groups to identify gaps in existing programs, and opportunities for improvement |  | • Number of co-curricular programs and services reviewed. • Number of assessments distributed, and results of assessments • Number of students with lived experience engaged in the review process | TO BE DEVELOPED
3.3 In collaboration with Academic, Student Union and other campus providers, complete a needs assessment for a digital record to help students thoughtfully select co-curricular engagement opportunities, integrate their campus experiences, communicate the development of skills, and reflect on their development in the areas of meaning and purpose. Build Understanding | • Director, Student Life | • Career Services • Service Learning • Residence Life | 1-2 years | • Complete needs assessment and recommendations |  |  | TO BE DEVELOPED
3.4 Strengthen off-campus student housing options, with a particular focus on facilitating off-campus accommodations for international students, in partnership with the Landlord’s Association and Town of Antigonish. This could include support for initiatives such as education about tenant rights and responsibilities, promotion of off-campus housing options, income tax support, and At Home in Antigonish for the Holidays program. Build Capacity | • VP, Students • Director, Student Life | • Manager, Restorative • Manager, Student Development | • 1-2 years
3.5 Develop targeted co-curricular programming for students with disabilities, with a focus on enhancing the first-year experience and experiential learning. Build Capacity | • Director, Health and Counselling | • Tramble Centre for Accessible Learning | 4-7 years | • Assemble a FYE Working Group, with sub-committee focused on transitions experiences for historically-excluded groups. • Develop program model and implementation strategy, informed by first-voice perspectives and and evidence-informed practices. |  | • Number of programs tailored to meet the needs of students with disabilities • Number of students with disabilities participating • Assessment of participant learning and growth | IN PROGRESS • StFX launched self-paced learning modules to provide all first-year students with transitional knowledge and skills. • StFX hired EDGE Coordinate to provide career support for students with disabilities.
3.6 Expand programming options for students with intellectual disabilities Build Capacity | • Director, Health and Counselling | • Tramble Centre for Accessible Learning | • 3 years | • Identify gaps in current support model for students with intellectual disabilities This can take place as part of the external review of accessibility supports and services. • Engage campus and community parnters in the needs assessment process, including first-voice perspectives. • Identify funding and resourcing requirements to implement desired models | • Program Funding • Promotions Materials *Opportunities for grant funding and/or donor support | • Completed needs assessment and resourcing plan | TO BE DEVELOPED
3.7 Design, develop and implement regular and ongoing training on equity and anti-racism for all StFX staff and students involved in leadership and peer positions. This training should: • Be relevant to different roles, departments and settings with a consistent focus on teaching anti-racism and decolonization, anti-discrimination, cultural competency/safety, equity, gender-based and sexual violence, mental health literacy/anti-stigma, resiliency, coping skills, and accessibility/ • Capture StFX values and occur on an ongoing basis to incorporate changes to policies, practices, and procedures. Build Capacity | • Director, Student Life | • Student Development • SVPRA • Wellness Education • DEC | 1-3 years | • Create online training modules for new staff and student leader onboarding • Develop scaffolded equity, anti-racism, and accessibility training program for all student leaders, including a combination of self-directed (online) and facilitated (in-person) learning opportunities • Formalize relationships with professional staff • Records of training are kept | • Employee Compensation (a dedicated position to provide oversight of peer leadership and track completion of training) • Oversight to include program development and other priority student groups (including distance and online learners). | • Number of students who engage in EDI-A programming each year. • Number of students who have taken disclosure training • Number of students who have taken Sexual Violence Policy training • Completed assessment of participant learning and growth • Collected feedback on training for improving learning and new content creation | IN PROGRESS • Developed and launched Xaverian Community Foundations modules offered to all first-year students and again to some student leaders (ex. CAs), including anti-racism module (You Belong @X) • Specialized training are available through the Diversity Engagement Centre • Revised SCA/CA training, tailoring content to reflect roles and responsibilities.
3.8 Increase the number of co-curricular engagement and paid employment opportunities available on campus, with a particular focus on expanding employment opportunities for students from historically-excluded students, including Indigenous, Black, minoritized, international, first-generation students, and students with disabilities. This should include: • Identifying, preventing and removing barriers to access current paid employment opportunities for students with disabilities, including paid internship and co-op placements. Build Capacity | • Director, Student Life | • Career Services | 4-7 years | • Identify barriers in existing paid employment, co-op and internship experiences for students with disabilities. • Identify partnership opportunities to expand paid employment opportunities for students with disabilities available on-campus • Identify and acquire funding to expand and diversify paid employment opportunities for students with disabilities | • Employee Compensation (Career Advisor, grant funded) | • Number of students with disabilities participating in paid employment opportunities on campus, internships and co-op placements. • Number of campus and community partners providing paid employment opportunities for students with disabilities • Assessment of student learning and satisfaction. | IN PROGRESS • Funding for EDGE has been added to the Province’s MOU to StFX. (haven’t heard how much as of today). The MOU is for four years. Within the last year, developed new employers based on students looking for a work experience that relate to student’s degree. Also developed new partnerships with businesses outside of Antigonish
3.9 Commit to equitable and inclusive recruitment, hiring, onboarding, retention and offboarding practices that increase the diversity among our student staff complements, in particular representation from Indigenous, Black, minoritized communities and persons with disabilities. Build Capacity | • Director, Student Life • Director, Human Rights and Equity • SLT | • HRERA • Career Services | • 1-12 months
3.10 Strengthen capacity of on-campus and off-campus employers to create culturally-relevant, trauma-informed and supportive workplaces. Build Capacity | • Director, Health and Counselling • Director, Human Rights and Equity | • Career Services • HRERA | • 1-2 years
3.11 Maintain the Student Accessibility Advisory Committee to provide leadership opportunities for students with disabilities and ensure that their voices and lived experienced are reflected in program and service design, development, and delivery. Build Connection | • Tramble Centre for Accessible Learning • Governance and Strategic Initiatives |  | • 1-12 months | • Ensure processes to continue the coordination of the StFX Student Accessibility Advisory Committee is in place | Member Compensation | • Number of student members • Number of committee meetings held per year | IN PROGRESS • Established committee structure and approved Terms of Reference • Members of Student Accessibility Advisory Committee met from Sep 2021 to present to inform the development of the StFX Accessibility Plan.
3.12 Maintain ongoing partnerships between StFX Career Services and Tramble Centre for Accessible Learning to provide students with disabilities with access to career mentorship, workplace connections and employability. Increase engagment in the Engage Develop, Grow Your Employability (EDGE) Program, and assess the impacts of the program on students with disabilities. Build Connection | • Director, Student Life • Director, Health and Counselling |  | • 1-12 months | • Maintain wage subsidy program for students with disabilities • Develop engaging career programming for students with disabilities (ex. workshops, panel discussions, etc.), including targeted programs for different faculties and groups. • Expand promotions for EDGE programming • Develop assessment strategy |  | • Number of student appointments per year • Number of unique student appointments per year • Students accessing EDGE Services per academic program • Number of placements • Students accessing EDGE Services per year of study • Average number of appointments per student • Assessment of participant learning and growth | IN PROGRESS • Funding for EDGE has been added to the Province’s MOU to StFX. (haven’t heard how much as of today). The MOU is for four years. Within the last year, developed new employers based on students looking for a work experience that relate to student’s degree. Also developed new partnerships with businesses outside of Antigonish
3.13 Establish strategic partnerships and collaborations with the Town of Antigonish and County partners to create a welcoming, equitable and accessible community environment for all StFX students, with a particular focus on facilitating community engagement and connection for students from historically-excluded groups. This includes Indigenous, Black, minoritized, 2SLGBTQIA+, international students, first generation students, and students with disabilities. This will involve collaborating on shared community projects, professional development, strengthening town-gown relations, and continuing to listen and learn from diverse student experiences. Build Connection